## Sheet1 (hidden)
1 drone 3 orang
5 drone 2 orang
orang
pengiriman
mobil
8 drone | 1 tim 2 drone (5 orang 1 mobil)

## Timeline
Tasks | Feb |  |  | Maret | [30 empty] | April
| 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | dst
Drone and Sparepart Preparation
Cargo Shipments (Logistic)
Team Fly in & Car Rental
Team Enter Site/Survey
Testing/Calibration (Initial Team)
Drone Ops (Initial Team)
Additional Team Ops
Off from Field (Temporary for Eid)
Kickstart Field Operations
Note on L4: 6 drones + spreaders + batteries
Note on AB4: Add equipments for ops
Note on AT4: Add 4 drones
Note on T5: Rent 1 ops car + 1 avanza
Note on AB5: Add equipment for ops
Note on T6: 5 orang 2tim (untuk uji coba)

## List Barang
LIST DRONE DAN SPAREPART
No | Item | Stok Target | Note | Kirim 1 | Jumlah | Kirim 2 | Jumlah | Stok Aktual | Kurang Stock
Main Parts
| Drone HD540 Pro | 1 |  | 2025-08-03 | 1 |  |  | 1 | 0
| Drone HD540 S | 9 |  | 2025-08-03 | 5 | 26/03/2025 | 4 | 9 | 0
| Remote Control | 10 |  | 2025-08-03 | 6 |  |  | 10 | 0
| Genset 10.000watt | 16 |  |  |  | 26/03/2025 | 2 | 2 | 14
| Tanki Spreader S | 16 |  |  | 1 | 26/03/2025 | 6 | 7 | 9
| TATTU 30.000mAh 18S Battery | 4 |  | 2025-08-03 | 4 |  |  | 4 | 0
| Swan Drone Smart Battery 68.4V/30000mAh 2.1kwh | 80 |  | 2025-08-03 | 16 | 26/03/2025 | 16 | 32 | 48
| Charger | 16 |  | 2025-08-03 | 8 | 26/03/2025 | 1 | 9 | 7
| Tanki Spreader Pro | 2 | Drone HD540 Pro | 2025-08-03 | 2 |  |  | 2 | 0
| Motor 2KW//65KV-2700 r/min CW | 16 |  | 2025-08-03 | 16 | 26/03/2025 | 1 | 17 | 0
| Motor 2KW//65KV-2700 r/min CCW | 16 |  | 2025-08-03 | 16 | 26/03/2025 | 1 | 17 | 0
| Skydroid Antenna | 12 |  | 2025-08-03 | 12 |  |  | 12 | 0
| Propeller 40 132 CCW | 32 | Carbon Fiber Sheet | 2025-08-03 | 32 | 26/03/2025 | 2 | 34 | 0
| Propeller 40 132 CW | 32 | Carbon Fiber Sheet | 2025-08-03 | 32 | 26/03/2025 | 2 | 34 | 0
| Radar Set (Agricultural Distance Recorder) | 5 |  | 2025-08-03 | 5 |  |  | 5 | 0
| Iron Pillar Frame Set | 1 | Pro Type | 2025-08-03 | 1 |  |  | 1 | 0
| Iron Pillar Frame Set | 2 | Super Type | 2025-08-03 | 2 |  |  | 2 | 0
| Carbon Fiber Tube Set | 10 | Super Type | 2025-08-03 | 10 |  |  | 10 | 0
| Tanki | 8 | Pro Type | 2025-03-05 | 2 | 2025-04-01 | 6 | 8 | 0
| Tanki | 8 | Super Type | 2025-03-05 | 1 | 2025-04-01 | 7 | 8 | 0
| Iron Pillar Frame (Distribution & Control Board) | 2 | Super Type | 2025-08-03 | 2 |  |  | 2 | 0
| Corong Uk.20cm | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| Obeng Plus Minus | 8 |  | 2025-08-03 | 6 | 26/03/2025 | 2 | 8 | 0
| Obeng Minus | 8 |  | 2025-08-03 | 4 | 26/03/2025 | 4 | 8 | 0
| Kunci T | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| Timah Solder | 8 |  | 2025-08-03 | 1 | 26/03/2025 | 7 | 8 | 0
| Kunci Inggris | 8 |  | 2025-08-03 | 2 |  | 6 | 8 | 0
| Obeng Bunga | 8 |  | 2025-08-03 | 1 | 26/03/2025 | 7 | 8 | 0
| Kunci Ring Pas 10 | 8 |  | 2025-08-03 | 2 | 26/03/2025 | 4 | 6 | 2
| Lotfett | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| Solder | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| Kunci Ring Pas 8 | 8 |  | 2025-08-03 | 2 | 26/03/2025 | 4 | 6 | 2
| Kunci L Set | 8 |  | 2025-08-03 | 8 |  |  | 8 | 0
| Tang Set | 8 |  | 2025-08-03 | 3 | 26/03/2025 | 2 | 5 | 3
| Dudukan Solder | 8 |  |  |  |  | 8 | 8 | 0
| Container Box Kecil Uk. (P x L x T) : 45 x 30 x 26.5 cm | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| Container Box Besar Uk. (P x L x T) : 70 cm x 48 cm x 42.5 cm | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| Container Box Sedang Uk. (P x L x T) : 55 x 38 x 34.5 cm | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| Kunci Busi Genset | 8 |  | 2025-08-03 | 1 | 26/03/2025 | 7 | 8 | 0
| APAR | 8 |  | 2025-08-03 | 1 | 26/03/2025 | 7 | 8 | 0
| Kunci Y 10-12-14 Inch | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| Kunci Y 8-10-12 Inch | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| BAOFENG BF-888S Set 2 Unit (2W) Walkie Talkie | 16 |  | 2025-08-03 | 12 | 26/03/2025 | 4 | 16 | 0
| Kanebo | 16 |  | 2025-08-03 | 1 | 26/03/2025 | 15 | 16 | 0
| APD-Kacamata Safety | 32 |  | 2025-08-03 | 10 | 26/03/2025 | 22 | 32 | 0
| APD-Rompi Safety | 32 |  | 2025-08-03 | 4 | 26/03/2025 | 28 | 32 | 0
| Terpal Biru 4 x 6 Meter | 16 |  |  |  | 26/03/2025 | 16 | 16 | 0
| Terpal Biru 3 x 4 Meter | 32 |  |  |  | 26/03/2025 | 32 | 32 | 0
| Tali Seling | 16 |  |  |  | 26/03/2025 | 16 | 16 | 0
| Toolbox | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| APD-Helm Safety | 32 |  | 2025-08-03 | 26 |  |  | 26 | 6
| APD-Sarung Tangan Safety Kain | 32 |  | 2025-08-03 | 32 |  |  | 32 | 0
| Anemometer | 8 |  | 2025-08-03 | 1 | 26/03/2025 | 8 | 9 | 0
| Glue Gun 100-240V 40W | 8 |  |  |  | 26/03/2025 | 8 | 8 | 0
| Multimeter | 8 |  |  |  | 26/03/2025 | 7 | 7 | 1
| Blower (battery) (untuk membersihkan tanki/debu) | 10 |  |  |  | 26/03/2025 | 8 | 8 | 2
| Kuas 5 inch | 12 |  |  |  | 26/03/2025 | 12 | 12 | 0

## List tim
| Drone 1 & Drone 2 | Keterangan | Diganti |  | Tim saat ini
1 | Fino Anperta | PKWTT |  |  | Man Power | 4
| Drone 3 & Drone 4 |  |  |  | Drone | 2
1 |  |  |  |  | Mobil | 1 | BPME
2 |  |  |  |  | Genset | 2
3 |  |  |  |  | Blower | 2
4
Tambahan
[5 empty] | Man Power | 12
| Drone 5 & Drone 6 |  |  |  | Drone | 6 | 2 BPME, 4 BPLE
1 |  |  |  |  | Genset | 3
2 |  |  |  |  | Blower | 6
3 |  |  |  |  | Mobil | 1 | BPME
4
[5 empty] | Perbandingan Sewa x beli genset |  | @bulan | [11 empty] | @12 bulan | Ongkir | Total/Tahun
| Drone 7 & Drone 8 |  |  |  | Capacity 30 Kva, 380/220 V, 3 Phase, 50 Hz, 1.500 Rpm, Pf 0,8 | 1 | 9435000 | 9435000 | 9435000 | 9435000 | 9435000 | 9435000 | 9435000 | 9435000 | 9435000 | 9435000 | 9435000 | 9435000 | 113220000 | 5000000 | 118220000
1 |  |  |  |  | MDG 38 RD ( 30 kw) - beli | 1 | 5625000 | 5625000 | 5625000 | 5625000 | 5625000 | 5625000 | 5625000 | 5625000 | 5625000 | 5625000 | 5625000 | 5625000 | 67500000 | 3350000 | 70850000
2 |  |  |  |  | MDG 30 RD ( 24 kw) - beli | 1 | 4916666.6667 | 4916666.6667 | 4916666.6667 | 4916666.6667 | 4916666.6667 | 4916666.6667 | 4916666.6667 | 4916666.6667 | 4916666.6667 | 4916666.6667 | 4916666.6667 | 4916666.6667 | 59000000 | 3350000 | 62350000
3
4
Ketersediaan Pilot yang bisa 4orang (dari spraying)
|  |  |  | Pilot | 4
|  |  |  | Training | 4
|  |  |  | BPLE | 8orang
|  |  |  | SAM 2 | selesai minggu ini |  | 8orang
Malako
Target 5 orang
keperluan untuk di follow UP ke SMF :
Ponton 2 untuk BPLE (untuk jalan 2 drone)
Pompom untuk alat kerja
|  |  |  | BPME | Pastikan keperluan di lapangan
Internal :
Perlu 8 orang (4 drone)
tanggal keberangatan ops 14 April
tanggal 13 genset
list barang yang sudah di site
merk firman 10rb

## List Mobil
LIST KENDARAAN OPERASIONAL RIAU
MOBIL
NO | PEMILIK LAMA | PLAT MOBIL | JENIS KENDARAAN | LOKASI SEKARANG | Warna | Tanggal Masuk
1 | Eka Delta Rent |  |  |  |  | 2025-05-13
2 | Eka Delta Rent |  |  |  |  | 2025-05-13
3 | Eka Delta Rent |  |  |  |  | 2025-04-01
4 | Eka Delta Rent |  |  |  |  | 2025-04-01
5 | Eka Delta Rent |  |  |  |  | 2025-04-01